Timeline for AADPRT 2026 Annual Meeting Program Chair

All actions by end of month unless specified date

PC = program chair

PCOM = program committee

March, 2025

- Set PCOM meeting day/times (including APA, AAP)

- Review meeting feedback

  - Whova

  - Jotform - plenaries

  - APA CME preliminary

- Theme/Title development

- Plenary speaker research

- PCOM Planning visit

- Meeting with PCOM and president to review recent meeting, discuss thoughts for upcoming meeting

- Schedule analysis: determine what to keep, eliminate, change

  - Plenaries

    - Keynote (Plenary #1)

    - Shein (Plenary #2)

    - Plenary #3

    - Plenary #4

    - Opening lunch/business meeting

    - ABPN/ACGME

    - President’s symposium

  - Career stage forums

    - NTD symposium/breakouts

    - Future training director

    - Early career

    - Mid-career

    - Late career

    - Past training director

  - Awards sessions: any changes to:

    - Posted information

    - Scripted information

    - Presenters

    - Staging

    - Session assignments

    - Committee member recognition

  - Abstract-selected workshops

    - number to include

    - ideal number of sessions

  - Posters

    - number to include

    - how and when to present: is 75-minutes appropriate?

  - Other

    - Allied association involvement: renew guaranteed workshop opportunity?

    - Academic Psychiatry involvement

    - Networking dinners

    - Consultations

    - Kenneth Hardy workshops

    - Rookie Reception

    - New and innovative ideas

April, 2025

- Theme/Title development

- Plenary speaker research

- Review preliminary schedule from ED

- If ready, share theme/title and plenary speaker ideas with SC

May, 2025

- Theme/Title finalized

- Plenary speaker research

- Back up plenary speaker research

- Abstract system and related webpages

  - Edits to forums/posters/workshops page due

  - Edits to abstract submission instructions for front of site and web portal due

  - Edits to FAQ due

- If moving forward with allied association pre-selected workshops

    - Confirm associations

    - Program chair extends invitation

    - Maintain policy? Participation does count toward the maximum of three workshops in which one may be a presenter

- Academic Psychiatry participation

- PCOM meeting topics

  - Edits to abstract submission system

  - Edits to abstract review system

  - Planning visit follow up

    - Flesh out Innovations Hub concept: abstract submission system, etc.

    - Flesh out advocacy concept

    - Poster quality improvement

  - Abstract system review (see above)

  - Schedule finalized

  - Master educator certification with participation in a certain number of workshops

  - Plenary speaker for innovation hub – what is process?

June, 2025

- Plenary speakers confirmed, handoff email sent, copying in ED – due June 6

- Back up plenary speaker research

- Paragraph or two introducing theme (for marketing/website) –include explanation of innovation hub

- Edit call for abstract review committee nominations language

- Review/edit abstract review committee nomination form: self-nominations only?

- Edit call for abstracts language

- Create/submit submission tips & innovation hub explanation power point deck for ED review prior to recording video – due 6/16

- Record video discussing submission tips, innovation hub, etc.

- Contact information for all pre-selected programming leaders and plenary speakers due to ED (ED to send invites with link to abstract submission form and deadlines early August with September 17 deadline)

- PCOM meeting topics

  - Review APA CME system final feedback

  - Review abstract system edits (submission and review)

  - Special interest tables

  - Committee table in the exhibitor area

July, 2025

*Awards system open 7/1 – 9/17

- Back up plenary speaker research

- Identify Shein lecturer, email them to alert them of title, give them explanation of meaning

- PCOM meeting topics

  - Workshop evaluators

  - Ribbons

    - Fun

    - Standard:

    - Add senior program directors?

    - New member ribbons?

    - EC ribbons – ask me?

  - Engaging first time attendees and new members beyond rookie reception?

  - Review of rookie reception: format changes?

  - Review final APA CME evaluation feedback from 25 meeting

August, 2025

*Abstract review committee nominations open 8/1 – 8/20

*Abstract system open 8/1 – 9/17

*Awards system open 7/1 – 9/17

*Program committee review of abstract review committee nominations 8/21 – 8/28

- Back up plenary speaker confirmed

- PC to market opening of abstract system via the Listserv (9/17 deadline) and abstract review committee nominations being accepted (8/20 deadline)

- Abstract review committee nominations reviewed by PCOM 8/21-8/28

- Abstract review committee notifications sent to nominees by PC Friday, 8/29.

- If moving forward, August 1, invitation to allied association liaisons regarding pre-selected workshops sent by PC chair including submission process (via abstract system) and participation policy (counts toward maximum of three workshops)

- Review abstract announcements

  - Poster acceptance

  - Poster rejection

  - Workshop acceptance

  - Workshop rejection

  - Career stage forum acceptance

  - Career stage forum rejection

- PC drafts innovation hub acceptance and rejection notifications

- PCOM meetings

  - # ACGME RC chair, Louise to discuss content

September, 2025

*Abstract system open 8/1 – 9/17

*Awards system open 7/1 – 9/17

*Abstract review 9/19-10/23

- 9/3, PC emails allied association representatives reminding of pending due date

- PC to market abstract system open via Listserv

- Abstracts due from pre-selected programming leaders 9/17

- Abstracts due from allied association pre-selected workshops 9/17

- Single page word document with meeting description for Academic Psychiatry Journal publication due 9/26 (published 12/1)

- Meeting with abstract review committee to prepare for review of abstracts no later than 9/16/25

- PC assigns abstract review committee members to poster v workshop review committee after reviewing number of submissions with listing to ED by 9/17.

- ED to assign committee members randomly to abstracts 9/18

- PCOM meetings

October, 2025

*Abstract review 9/19-10/23

*Room block opens 10/1

*Abstract and award selection announcements released 10/31

- Abstract selections due 10/23 including career stage forum and innovation hub selections

- Workshop session assignments completed by PC-elect and to ED and PCOM 10/28 for review (to ensure no duplication of speaker in one session)

- Workshop session assignments review completed 10/30

- Identification of programming for audiences: residents, PAs, NTDs due 10/30

- Begin work on accreditation application

- PC markets hotel room block open via listserv

- Review/revise “annual meeting guide deck” (how to register, book hotel, how to prepare) and to ED by 10/11.

- Record annual meeting guide presentation video

- PCOM meetings

  - Abstract submission/review system feedback

November, 2025

*Awardee materials due 11/12

- Completion of accreditation application

- PC to announce on listserv abstract notifications have been released

- Identify plenary session moderators

- PCOM meetings

  - Revised program evaluation questions due for APA CME link

  - Revised program evaluation questions due for non-plenary programming

  - Revised program evaluation questions due for plenaries

December, 2025

*Speaker reveal week 12/1 – 12/4

*Registration opens 12/4

*Nominations open for program chair-elect 12/4

*Poster contest opens 12/4

- PC emails EC 12/4 to encourage early registration so as to identify system issues

- PC market room block on listserv

- Review presenter conflict of interest and complete Management of Conflict of Interest form

- PCOM meetings

January, 2026

*Registration rate increases 1/9

*Program chair-elect nominations close 1/8

*Poster contest/artwork deadline 1/14

*Poster contest committee review 1/16 - 1/30

- PC markets plenary speakers on listserv along with suggested reading (first two weeks of January)

- PC markets end of early bird rate prior to 1/9 on listserv

- PC markets last call for rooms on listserv (1/31/26)

- Plenary speaker introductions finalized and to ED

- Meeting with plenary session moderators

  - Responsibility to review bio and prepare questions

  - Join PCOM at their table during session

  - Participate in rehearsal

- PCOM meetings

February, 2026

*Room block closes 2/7 or earlier if full

*Registration closes and 50% refund for cancellation ends 2/5

*Networking dinner restaurant sign up 2/6-2/20

*Speaker power points due 2/12

- PC markets end of pre-registration (2/5)

- Power point slides due or review of decks prepared by ED 2/12

- Plenary scripts due

- PCOM meetings, if needed

March, 2026

*Annual Meeting 3/2 - 3/6

- Hotel pre-con meeting 2/27, morning.  Please plan to attend (typically an hour)

- During meeting: PA and NTD symposia welcomes

- SLEEP, VACATION, BE HAPPY YOU SURVIVED!

General

- Support ED marketing efforts with posting of information to listserv